## 내용
LG전자 N-ERP 프로젝트 | [12 empty] | 3자테스트 결함내역
프로그램ID |  | ZCBMR2400 |  |  |  |  | 프로그램명 | 투자 프로젝트별 감가상각 시뮬레이션 관리
테스트 담당자 |  | Nguyen Manh Tri | 테스트 단게 | 3자테스트 | 테스트 차수 | 1 | 테스트일 | 2024-05-13 | 결함건수 | 1 | 설계자 확인 | 조치완료
No | 결함 내역 요약 | [10 empty] | 상태
1 | Function: Project start year search condition does not match Function: Can not get all the records when the Depre. Simulation Id search condition is empty | [10 empty] | 결함
3 | Function: Searching with Project Management to Depreciation choice throw Project Base Date required error | [10 empty] | 결함
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Defect 1
Case 3: | Project start year search condition does not match

## Defect 2
Case 4: | Function: Can not get all the records when the Depre. Simulation Id search condition is empty
When Depreciation Simulation Id condition is not empty, each Depreciation Simulation Id has an unique record but when that search field is empty, only one record is returned
When condition is empty

## Defect 3
Case 1: | Function: Searching with Project Management to Depreciation choice throw Project Base Date required error